## Sheet1
Worklog Id | Issue Key | Issue Summary | Issue Status | Time spent | Time Spent (seconds) | Started at | Updated at | Comment | Author | Author's Account Id | Project Key | Project Name | Components | Labels | Epic Key | Epic Summary | Issue Type | Original Estimate | Original Estimate (seconds) | Remaining Estimate | Remaining Estimate (seconds) | Due Date | Parent Key | Parent Summary | Story Points | Fix Versions
10000 | COD-5 | GIT policy kialakítása | Kész | 00:56 | 3360 | 2023-06-15T04:00:00+02:00 | 2023-06-16T09:04:36+02:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10001 | COD-7 | Kezdetleges design készítés | Kész | 01:00 | 3600 | 2023-06-16T12:21:54+02:00 | 2023-06-16T13:22:33+02:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10002 | COD-7 | Kezdetleges design készítés | Kész | 00:20 | 1200 | 2023-06-16T13:37:54+02:00 | 2023-06-16T13:58:02+02:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10003 | COD-4 | Részletes leírás készítése a projectről | Kész | 01:00 | 3600 | 2023-06-18T17:42:21+02:00 | 2023-06-18T18:42:40+02:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10004 | COD-8 | Branchek létrehozása | Kész | 00:02 | 120 | 2023-06-18T19:56:27+02:00 | 2023-06-18T19:59:27+02:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10011 | COD-10 | DB diagram kidolgozása | Kész | 03:00 | 10800 | 2023-06-19T09:00:00+02:00 | 2023-06-27T10:45:57+02:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10005 | COD-7 | Kezdetleges design készítés | Kész | 00:50 | 3000 | 2023-06-19T10:12:54+02:00 | 2023-06-19T11:03:15+02:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10006 | COD-7 | Kezdetleges design készítés | Kész | 00:50 | 3000 | 2023-06-19T14:12:10+02:00 | 2023-06-19T15:02:18+02:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10007 | COD-9 | Backup policy kialakítása | Kész | 01:04 | 3840 | 2023-06-22T18:54:46+02:00 | 2023-06-22T20:00:49+02:00 | Biztonsági mentési szabályzat | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10008 | COD-7 | Kezdetleges design készítés | Kész | 00:20 | 1200 | 2023-06-23T16:20:32+02:00 | 2023-06-23T16:40:41+02:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10009 | COD-9 | Backup policy kialakítása | Kész | 00:42 | 2520 | 2023-06-26T21:03:46+02:00 | 2023-06-26T21:46:36+02:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10010 | COD-10 | DB diagram kidolgozása | Kész | 03:00 | 10800 | 2023-06-27T07:42:00+02:00 | 2023-06-27T10:42:04+02:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10012 | COD-8 | Branchek létrehozása | Kész | 00:08 | 480 | 2023-06-27T10:55:15+02:00 | 2023-06-27T11:03:37+02:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10013 | COD-7 | Kezdetleges design készítés | Kész | 00:15 | 900 | 2023-06-27T12:24:09+02:00 | 2023-06-27T12:39:15+02:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10014 | COD-9 | Backup policy kialakítása | Kész | 00:20 | 1200 | 2023-09-19T10:19:32+02:00 | 2023-09-19T10:40:08+02:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10015 | COD-11 | Végpontok létrehozása | Kész | 01:00 | 3600 | 2023-09-25T13:31:43+02:00 | 2023-09-25T14:31:56+02:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10016 | COD-11 | Végpontok létrehozása | Kész | 01:15 | 4500 | 2023-09-25T15:33:11+02:00 | 2023-09-25T16:49:26+02:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10017 | COD-15 | SQL táblák elkészítése | Kész | 02:00 | 7200 | 2023-09-26T07:32:08+02:00 | 2023-09-26T09:32:46+02:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10018 | COD-16 | SQL CRUD műveletek megírása | Kész | 00:40 | 2400 | 2023-09-26T08:57:29+02:00 | 2023-09-26T09:37:56+02:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10019 | COD-17 | SQL táblák javítása és új tárolt eljárások | Kész | 00:45 | 2700 | 2023-09-26T09:02:43+02:00 | 2023-09-26T09:49:37+02:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10020 | COD-11 | Végpontok létrehozása | Kész | 01:30 | 5400 | 2023-09-26T09:24:34+02:00 | 2023-09-26T10:54:54+02:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10021 | COD-11 | Végpontok létrehozása | Kész | 01:10 | 4200 | 2023-09-26T11:38:18+02:00 | 2023-09-26T12:48:34+02:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10024 | COD-13 | Főoldal HTML/CSS/JS | Kész | 02:00 | 7200 | 2023-09-26T11:42:35+02:00 | 2023-09-26T13:42:42+02:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10026 | COD-17 | SQL táblák javítása és új tárolt eljárások | Kész | 01:15 | 4500 | 2023-09-26T12:39:36+02:00 | 2023-09-26T13:54:58+02:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10022 | COD-11 | Végpontok létrehozása | Kész | 00:10 | 600 | 2023-09-26T13:02:40+02:00 | 2023-09-26T13:12:58+02:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10025 | COD-17 | SQL táblák javítása és új tárolt eljárások | Kész | 00:15 | 900 | 2023-09-26T13:31:45+02:00 | 2023-09-26T13:47:21+02:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10027 | COD-11 | Végpontok létrehozása | Kész | 01:00 | 3600 | 2023-10-02T20:17:34+02:00 | 2023-10-02T21:17:50+02:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10028 | COD-11 | Végpontok létrehozása | Kész | 01:10 | 4200 | 2023-10-03T09:39:47+02:00 | 2023-10-03T10:50:30+02:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10030 | COD-18 | Login HTML/CSS/JS | Kész | 02:00 | 7200 | 2023-10-03T11:06:25+02:00 | 2023-10-03T13:06:29+02:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10029 | COD-13 | Főoldal HTML/CSS/JS | Kész | 01:00 | 3600 | 2023-10-03T12:05:00+02:00 | 2023-10-03T13:05:10+02:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10031 | COD-11 | Végpontok létrehozása | Kész | 01:10 | 4200 | 2023-10-15T19:32:23+02:00 | 2023-10-15T20:42:31+02:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10032 | COD-11 | Végpontok létrehozása | Kész | 02:10 | 7800 | 2023-10-16T17:57:47+02:00 | 2023-10-16T20:08:00+02:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10033 | COD-13 | Főoldal HTML/CSS/JS | Kész | 03:00 | 10800 | 2023-10-17T13:24:32+02:00 | 2023-10-17T16:24:37+02:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10034 | COD-19 | Termék oldal készítése | Kész | 01:40 | 6000 | 2023-10-17T18:20:18+02:00 | 2023-10-17T20:00:31+02:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10035 | COD-19 | Termék oldal készítése | Kész | 02:00 | 7200 | 2023-10-19T17:53:37+02:00 | 2023-10-19T19:53:50+02:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10036 | COD-19 | Termék oldal készítése | Kész | 00:30 | 1800 | 2023-10-20T19:33:34+02:00 | 2023-10-20T20:03:40+02:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10037 | COD-11 | Végpontok létrehozása | Kész | 00:20 | 1200 | 2023-10-24T10:00:51+02:00 | 2023-10-24T10:20:56+02:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10038 | COD-21 | Összes Termék oldal Ár szűrés , termékek meg jelenítése CSS/JavaScript | Kész | 02:30 | 9000 | 2023-10-26T10:01:49+02:00 | 2023-10-26T12:32:18+02:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10039 | COD-22 | Összes termék oldal - Kosár (HTML/CSS) | Kész | 02:00 | 7200 | 2023-10-26T10:32:19+02:00 | 2023-10-26T12:32:25+02:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10040 | COD-20 | Összes termék oldal - Szűrők (HTML/CSS) | Kész | 02:00 | 7200 | 2023-10-26T10:32:48+02:00 | 2023-10-26T12:32:51+02:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10041 | COD-20 | Összes termék oldal - Szűrők (HTML/CSS) | Kész | 00:30 | 1800 | 2023-10-26T12:02:54+02:00 | 2023-10-26T12:33:01+02:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10042 | COD-21 | Összes Termék oldal Ár szűrés , termékek meg jelenítése CSS/JavaScript | Kész | 02:00 | 7200 | 2023-10-27T17:36:23+02:00 | 2023-10-27T19:36:20+02:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10043 | COD-11 | Végpontok létrehozása | Kész | 00:30 | 1800 | 2023-10-31T14:29:21+01:00 | 2023-10-31T14:59:28+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10044 | COD-24 | Játékok oldal tesztelése | Kész | 01:50 | 6600 | 2023-11-06T12:24:33+01:00 | 2023-11-06T14:14:42+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10045 | COD-23 | Regisztráció HTML/CSS/JS | Kész | 01:20 | 4800 | 2023-11-06T13:40:59+01:00 | 2023-11-06T15:01:06+01:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10046 | COD-25 | Belépés/Regisztráció hibajavítás | Kész | 02:20 | 8400 | 2023-11-09T16:49:12+01:00 | 2023-11-09T19:09:19+01:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10047 | COD-26 | Játék oldal létrehozása és összekötése a backenddel | Kész | 00:35 | 2100 | 2023-11-09T20:56:56+01:00 | 2023-11-09T21:32:06+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10048 | COD-26 | Játék oldal létrehozása és összekötése a backenddel | Kész | 02:30 | 9000 | 2023-11-10T08:16:35+01:00 | 2023-11-10T10:46:42+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10049 | COD-26 | Játék oldal létrehozása és összekötése a backenddel | Kész | 01:20 | 4800 | 2023-11-10T14:04:49+01:00 | 2023-11-10T15:24:57+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10050 | COD-26 | Játék oldal létrehozása és összekötése a backenddel | Kész | 01:00 | 3600 | 2023-11-10T15:30:38+01:00 | 2023-11-10T16:30:45+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10051 | COD-25 | Belépés/Regisztráció hibajavítás | Kész | 02:00 | 7200 | 2023-11-10T17:11:38+01:00 | 2023-11-10T19:11:44+01:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10052 | COD-27 | Belépés és regisztráció oldal ketté szedése és figma design | Kész | 01:00 | 3600 | 2023-11-10T18:13:34+01:00 | 2023-11-10T19:13:40+01:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10054 | COD-28 | Játék és ajándékkártya létrehozása | Kész | 01:10 | 4200 | 2023-11-11T13:09:38+01:00 | 2023-11-11T14:19:49+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10053 | COD-29 | Táblák feltöltése | Kész | 00:10 | 600 | 2023-11-11T13:36:09+01:00 | 2023-11-11T13:46:35+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10055 | COD-34 | Ajándék kártya oldal létrehozása | Kész | 00:25 | 1500 | 2023-11-11T14:46:19+01:00 | 2023-11-11T15:11:25+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10056 | COD-35 | Projekt ötlet szerkesztése | Kész | 00:30 | 1800 | 2023-11-11T15:30:00+01:00 | 2023-11-11T16:00:05+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10057 | COD-35 | Projekt ötlet szerkesztése | Kész | 00:10 | 600 | 2023-11-11T17:51:19+01:00 | 2023-11-11T18:01:22+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10059 | COD-35 | Projekt ötlet szerkesztése | Kész | 00:20 | 1200 | 2023-11-11T21:42:28+01:00 | 2023-11-11T22:02:35+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10060 | COD-13 | Főoldal HTML/CSS/JS | Kész | 01:00 | 3600 | 2023-11-11T23:55:18+01:00 | 2023-11-12T00:55:23+01:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10061 | COD-35 | Projekt ötlet szerkesztése | Kész | 00:20 | 1200 | 2023-11-12T13:50:45+01:00 | 2023-11-12T14:10:50+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10062 | COD-35 | Projekt ötlet szerkesztése | Kész | 00:20 | 1200 | 2023-11-12T14:32:51+01:00 | 2023-11-12T14:52:55+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10063 | COD-30 | Tárolt eljárások átalakítása | Kész | 01:10 | 4200 | 2023-11-12T15:21:16+01:00 | 2023-11-12T16:31:46+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10064 | COD-34 | Ajándék kártya oldal létrehozása | Kész | 01:20 | 4800 | 2023-11-12T17:07:29+01:00 | 2023-11-12T18:27:34+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10067 | COD-37 | termekek tárolt eljárás létrehozása | Kész | 02:00 | 7200 | 2023-11-13T11:50:50+01:00 | 2023-11-13T13:50:53+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10065 | COD-42 | jatek és ajandekkartya végpont javítása | Kész | 00:25 | 1500 | 2023-11-13T13:20:26+01:00 | 2023-11-13T13:45:31+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10070 | COD-38 | Navigáció fixálása | Kész | 02:00 | 7200 | 2023-11-13T13:32:08+01:00 | 2023-11-13T15:32:10+01:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10069 | COD-31 | Diagram egyeztetése | Kész | 01:30 | 5400 | 2023-11-13T13:40:33+01:00 | 2023-11-13T15:10:38+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10066 | COD-39 | korhatar mező javítása | Kész | 00:05 | 300 | 2023-11-13T13:45:11+01:00 | 2023-11-13T13:50:17+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10068 | COD-42 | jatek és ajandekkartya végpont javítása | Kész | 00:15 | 900 | 2023-11-13T13:45:40+01:00 | 2023-11-13T14:00:47+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10072 | COD-40 | termekek végpont létrehozása | Kész | 00:20 | 1200 | 2023-11-13T18:30:45+01:00 | 2023-11-13T18:50:51+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10073 | COD-36 | Újabb Játék és ajándékkártya létrehozása | Kész | 01:20 | 4800 | 2023-11-13T21:43:18+01:00 | 2023-11-13T23:03:27+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10074 | COD-42 | jatek és ajandekkartya végpont javítása | Kész | 01:00 | 3600 | 2023-11-14T11:35:11+01:00 | 2023-11-14T12:35:15+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10075 | COD-49 | Carousel kódolása | Kész | 01:30 | 5400 | 2023-11-15T13:10:50+01:00 | 2023-11-15T14:40:59+01:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10076 | COD-51 | Carousel megtervezése | Kész | 00:40 | 2400 | 2023-11-15T14:27:44+01:00 | 2023-11-15T15:07:49+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10077 | COD-53 | Főoldal végpont létrehozása | Kész | 00:20 | 1200 | 2023-11-15T15:10:45+01:00 | 2023-11-15T15:30:49+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10078 | COD-52 | Főoldal összekötése a backenddel | Kész | 01:40 | 6000 | 2023-11-15T15:43:45+01:00 | 2023-11-15T17:23:54+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10079 | COD-43 | Tárolt eljárások készítése | Kész | 00:30 | 1800 | 2023-11-15T17:35:59+01:00 | 2023-11-15T18:06:05+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10080 | COD-50 | Felhasználó lenyíló fül dizájn módosítás | Kész | 00:15 | 900 | 2023-11-16T11:33:00+01:00 | 2023-11-16T11:34:00+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10081 | COD-41 | Termékek oldal összekötése a backend-del | Kész | 00:40 | 2400 | 2023-11-17T16:32:42+01:00 | 2023-11-17T17:12:45+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10082 | COD-44 | Kosár oldal megvalósítása | Kész | 02:10 | 7800 | 2023-11-17T20:09:24+01:00 | 2023-11-17T22:19:46+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10083 | COD-46 | Lábléc kialakítása | Kész | 00:10 | 600 | 2023-11-18T11:30:44+01:00 | 2023-11-18T11:40:50+01:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10084 | COD-59 | Kosár újratervezése | Kész | 00:30 | 1800 | 2023-11-18T13:21:24+01:00 | 2023-11-18T13:51:25+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10085 | COD-60 | Felhasználó oldal megtervezése | Kész | 00:30 | 1800 | 2023-11-18T13:46:42+01:00 | 2023-11-18T14:16:45+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10086 | COD-60 | Felhasználó oldal megtervezése | Kész | 00:30 | 1800 | 2023-11-18T14:29:06+01:00 | 2023-11-18T14:59:11+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10087 | COD-25 | Belépés/Regisztráció hibajavítás | Kész | 02:00 | 7200 | 2023-11-18T15:52:31+01:00 | 2023-11-18T17:52:37+01:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10088 | COD-49 | Carousel kódolása | Kész | 00:30 | 1800 | 2023-11-18T17:23:32+01:00 | 2023-11-18T17:53:37+01:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10090 | COD-56 | felhasználó tábla javítása | Kész | 00:20 | 1200 | 2023-11-18T18:51:05+01:00 | 2023-11-18T19:11:10+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10089 | COD-31 | Diagram egyeztetése | Kész | 00:10 | 600 | 2023-11-18T18:58:55+01:00 | 2023-11-18T19:09:03+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10091 | COD-48 | Keresőmező | Kész | 04:00 | 14400 | 2023-11-19T14:39:23+01:00 | 2023-11-19T18:39:28+01:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10092 | COD-54 | kosar tárolt eljárás létrehozása | Kész | 01:20 | 4800 | 2023-11-19T19:02:10+01:00 | 2023-11-19T20:22:14+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10093 | COD-55 | Kosár oldal megvalósítása | Kész | 02:40 | 9600 | 2023-11-19T20:02:56+01:00 | 2023-11-19T22:43:02+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10094 | COD-58 | kód felülvizsgálata | Kész | 01:00 | 3600 | 2023-11-20T10:08:13+01:00 | 2023-11-20T11:08:17+01:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10095 | COD-62 | Felhasználó oldal megvalósítása | Kész | 01:50 | 6600 | 2023-11-20T14:54:11+01:00 | 2023-11-20T16:44:21+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10096 | COD-11 | Végpontok létrehozása | Kész | 00:40 | 2400 | 2023-11-23T13:27:08+01:00 | 2023-11-23T14:07:13+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10097 | COD-35 | Projekt ötlet szerkesztése | Kész | 00:20 | 1200 | 2023-11-23T13:52:02+01:00 | 2023-11-23T14:12:06+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10099 | COD-65 | Bejelentkezés megvalósítása | Kész | 02:00 | 7200 | 2023-11-24T16:59:57+01:00 | 2023-11-24T18:59:59+01:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10098 | COD-66 | Főoldal javítása | Kész | 00:30 | 1800 | 2023-11-24T18:29:37+01:00 | 2023-11-24T18:59:47+01:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10100 | COD-63 | Adatbázis javítása | Kész | 00:05 | 300 | 2023-11-24T22:55:57+01:00 | 2023-11-24T23:01:01+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10101 | COD-54 | kosar tárolt eljárás létrehozása | Kész | 01:00 | 3600 | 2023-11-26T23:42:31+01:00 | 2023-11-27T00:42:37+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10102 | COD-64 | kosar tárolt eljárás javítása | Kész | 00:30 | 1800 | 2023-11-27T00:12:49+01:00 | 2023-11-27T00:42:52+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10103 | COD-68 | Tokenek előkészítése | Kész | 02:30 | 9000 | 2023-11-27T09:08:41+01:00 | 2023-11-27T11:38:46+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10104 | COD-64 | kosar tárolt eljárás javítása | Kész | 00:15 | 900 | 2023-11-28T20:07:26+01:00 | 2023-11-28T20:22:30+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10105 | COD-70 | Indexek nevének átírása | Kész | 00:35 | 2100 | 2023-11-29T10:40:52+01:00 | 2023-11-29T11:16:08+01:00 |  | Dávid Gitt | 712020:156dd8ca-a798-418b-a64b-893776de4cc3 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10106 | COD-69 | Tárolt eljárások a validációhoz | Kész | 00:50 | 3000 | 2023-11-29T11:21:51+01:00 | 2023-11-29T12:12:04+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10107 | COD-64 | kosar tárolt eljárás javítása | Kész | 00:10 | 600 | 2023-11-30T19:10:05+01:00 | 2023-11-30T19:20:12+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10108 | COD-74 | rendeles tábla módosítása | Kész | 00:10 | 600 | 2023-11-30T19:14:24+01:00 | 2023-11-30T19:24:28+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10109 | COD-71 | rendeles tárolt eljárás | Kész | 00:40 | 2400 | 2023-11-30T19:14:42+01:00 | 2023-11-30T19:54:54+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10110 | COD-71 | rendeles tárolt eljárás | Kész | 00:30 | 1800 | 2023-11-30T19:41:46+01:00 | 2023-11-30T20:11:51+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10111 | COD-73 | kosar tábla módosítása | Kész | 00:05 | 300 | 2023-11-30T20:15:57+01:00 | 2023-11-30T20:21:01+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10112 | COD-71 | rendeles tárolt eljárás | Kész | 00:05 | 300 | 2023-11-30T20:16:32+01:00 | 2023-11-30T20:21:38+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10113 | COD-72 | Játékok létrehozása | Kész | 01:23 | 4980 | 2023-12-01T18:00:47+01:00 | 2023-12-01T19:23:56+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10114 | COD-72 | Játékok létrehozása | Kész | 00:53 | 3180 | 2023-12-02T17:20:17+01:00 | 2023-12-02T18:13:31+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10115 | COD-77 | kosar végpont megvalósítása | Kész | 01:40 | 6000 | 2023-12-02T18:54:11+01:00 | 2023-12-02T20:34:17+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10116 | COD-77 | kosar végpont megvalósítása | Kész | 01:40 | 6000 | 2023-12-03T15:41:39+01:00 | 2023-12-03T17:21:49+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10117 | COD-35 | Projekt ötlet szerkesztése | Kész | 00:20 | 1200 | 2023-12-03T20:14:00+01:00 | 2023-12-03T20:14:53+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10118 | COD-35 | Projekt ötlet szerkesztése | Kész | 00:45 | 2700 | 2023-12-03T20:14:00+01:00 | 2023-12-03T20:15:15+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10121 | COD-65 | Bejelentkezés megvalósítása | Kész | 02:00 | 7200 | 2023-12-04T07:58:04+01:00 | 2023-12-04T09:58:10+01:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10120 | COD-47 | Játék és ajándékkártya oldal javítása | Kész | 01:00 | 3600 | 2023-12-04T08:57:53+01:00 | 2023-12-04T09:57:58+01:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10119 | COD-78 | Lábléc javítása | Kész | 00:10 | 600 | 2023-12-04T09:47:27+01:00 | 2023-12-04T09:57:41+01:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10122 | COD-80 | Bejelentkezés és regisztrációs átírányítás javítása | Kész | 00:10 | 600 | 2023-12-04T09:52:14+01:00 | 2023-12-04T10:02:24+01:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10123 | COD-81 | Ajándék kártyák törlése az adatbázisból | Kész | 00:26 | 1560 | 2023-12-05T17:44:40+01:00 | 2023-12-05T18:11:03+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10124 | COD-82 | Navbar elemeinek törlése | Kész | 00:10 | 600 | 2023-12-05T18:48:10+01:00 | 2023-12-05T18:58:09+01:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10125 | COD-35 | Projekt ötlet szerkesztése | Kész | 00:15 | 900 | 2023-12-05T18:52:57+01:00 | 2023-12-05T19:08:05+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10126 | COD-81 | Ajándék kártyák törlése az adatbázisból | Kész | 00:10 | 600 | 2023-12-05T23:11:20+01:00 | 2023-12-05T23:21:23+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10127 | COD-84 | Főoldal mobil nézet megtervezése | Kész | 00:50 | 3000 | 2023-12-06T15:17:18+01:00 | 2023-12-06T16:07:23+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10128 | COD-83 | Ajándék kártyák törlése a backendről | Kész | 00:10 | 600 | 2023-12-06T16:11:36+01:00 | 2023-12-06T16:21:40+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10129 | COD-35 | Projekt ötlet szerkesztése | Kész | 00:10 | 600 | 2023-12-06T16:20:30+01:00 | 2023-12-06T16:30:34+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10130 | COD-35 | Projekt ötlet szerkesztése | Kész | 00:20 | 1200 | 2023-12-06T16:59:26+01:00 | 2023-12-06T17:19:35+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10131 | COD-86 | Felhasználási feltételek oldal | Kész | 00:35 | 2100 | 2023-12-10T19:21:18+01:00 | 2023-12-10T19:56:21+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10136 | COD-91 | Termékek mobil nézet megtervezése | Kész | 03:30 | 12600 | 2023-12-11T12:08:33+01:00 | 2023-12-11T15:38:44+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10132 | COD-87 | Tesztek készítése | Kész | 02:20 | 8400 | 2023-12-11T12:44:40+01:00 | 2023-12-11T15:04:56+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10133 | COD-88 | Főoldal reszponzívvá tétele | Kész | 02:00 | 7200 | 2023-12-11T13:22:55+01:00 | 2023-12-11T15:23:00+01:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10134 | COD-58 | kód felülvizsgálata | Kész | 02:00 | 7200 | 2023-12-11T13:25:52+01:00 | 2023-12-11T15:25:57+01:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10135 | COD-76 | Képek javítása frontend szinten | Kész | 00:30 | 1800 | 2023-12-11T14:56:16+01:00 | 2023-12-11T15:26:26+01:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10137 | COD-87 | Tesztek készítése | Kész | 01:30 | 5400 | 2023-12-12T10:54:50+01:00 | 2023-12-12T12:24:54+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10139 | COD-93 | Termékek reszponzívvá tétele | Kész | 03:30 | 12600 | 2023-12-12T11:15:18+01:00 | 2023-12-12T14:45:27+01:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10138 | COD-94 | Kosár mobil nézet megtervezése | Kész | 00:30 | 1800 | 2023-12-12T12:54:31+01:00 | 2023-12-12T13:24:36+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10140 | COD-95 | Bejelentkezés, regisztráció átirányítások | Kész | 00:25 | 1500 | 2023-12-12T15:37:38+01:00 | 2023-12-12T16:02:43+01:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10144 | COD-98 | Kosár összekötése a backenddel | Kész | 06:00 | 21600 | 2023-12-13T10:18:16+01:00 | 2023-12-13T16:18:24+01:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10141 | COD-96 | Felhasznaló tábla id mezőjének javítása | Kész | 00:10 | 600 | 2023-12-13T11:34:16+01:00 | 2023-12-13T11:44:22+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10142 | COD-87 | Tesztek készítése | Kész | 00:50 | 3000 | 2023-12-13T12:41:05+01:00 | 2023-12-13T13:31:16+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10143 | COD-97 | Játék mobil nézet megtervezése | Kész | 00:20 | 1200 | 2023-12-13T13:57:03+01:00 | 2023-12-13T14:17:07+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10145 | COD-101 | Rendelés megvalósítása adatbázis szinten | Kész | 01:35 | 5700 | 2023-12-14T12:03:56+01:00 | 2023-12-14T13:39:01+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10146 | COD-100 | Termékek reszponzívvá tétele | Kész | 02:00 | 7200 | 2023-12-14T12:10:42+01:00 | 2023-12-14T14:10:47+01:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10147 | COD-57 | felhasználó fül életre keltése | Kész | 02:00 | 7200 | 2023-12-14T12:11:29+01:00 | 2023-12-14T14:11:36+01:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10148 | COD-98 | Kosár összekötése a backenddel | Kész | 01:00 | 3600 | 2023-12-14T13:11:55+01:00 | 2023-12-14T14:12:00+01:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10149 | COD-103 | Felhasználó mobil nézet megtervezése | Kész | 00:15 | 900 | 2023-12-14T13:57:06+01:00 | 2023-12-14T14:12:12+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10150 | COD-87 | Tesztek készítése | Kész | 01:10 | 4200 | 2023-12-14T19:29:39+01:00 | 2023-12-14T20:39:48+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10153 | COD-104 | Felhasználó reszponzívvá tétele | Kész | 03:00 | 10800 | 2023-12-15T07:43:00+01:00 | 2023-12-15T10:43:09+01:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10152 | COD-99 | Kosár reszponzívvá tétele | Kész | 02:00 | 7200 | 2023-12-15T08:39:44+01:00 | 2023-12-15T10:39:47+01:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10154 | COD-102 | Rendelés megvalósítása backend szinten | Kész | 06:15 | 22500 | 2023-12-15T10:06:46+01:00 | 2023-12-15T16:22:43+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10151 | COD-102 | Rendelés megvalósítása backend szinten | Kész | 00:15 | 900 | 2023-12-15T10:10:25+01:00 | 2023-12-15T10:25:30+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10155 | COD-87 | Tesztek készítése | Kész | 00:45 | 2700 | 2023-12-15T22:10:55+01:00 | 2023-12-15T22:56:18+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10156 | COD-102 | Rendelés megvalósítása backend szinten | Kész | 05:00 | 18000 | 2023-12-17T13:52:43+01:00 | 2023-12-17T18:52:48+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10157 | COD-102 | Rendelés megvalósítása backend szinten | Kész | 02:00 | 7200 | 2023-12-18T09:24:11+01:00 | 2023-12-18T11:24:16+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10158 | COD-106 | Felhasználó végpont javítása backend szinten | Kész | 00:45 | 2700 | 2023-12-19T13:58:12+01:00 | 2023-12-19T14:43:18+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10159 | COD-107 | Token megvalóítása backend szinten | Kész | 02:00 | 7200 | 2023-12-20T15:11:42+01:00 | 2023-12-20T17:11:46+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10160 | COD-108 | JUnit tesztek készítése | Kész | 04:00 | 14400 | 2024-01-08T09:13:08+01:00 | 2024-01-08T13:13:57+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10161 | COD-121 | Nem használt tárolt eljárások törlése | Kész | 00:45 | 2700 | 2024-01-23T10:09:24+01:00 | 2024-01-23T10:54:28+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10163 | COD-125 | Bestseller előkészítése adatbázis szinten | Kész | 00:40 | 2400 | 2024-01-23T10:15:09+01:00 | 2024-01-23T10:55:07+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10164 | COD-128 | Nem használt végpontok és hozzájuk kapcsolódó függvények, metódusok törlése | Kész | 00:35 | 2100 | 2024-01-23T10:25:13+01:00 | 2024-01-23T11:00:18+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10162 | COD-126 | Admin lehetőség törlése adatbázis szinten | Kész | 00:10 | 600 | 2024-01-23T10:44:55+01:00 | 2024-01-23T10:54:52+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10165 | COD-127 | Admin lehetőség törlése backend szinten | Kész | 00:05 | 300 | 2024-01-23T10:55:44+01:00 | 2024-01-23T11:00:50+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10166 | COD-131 | Bestseller előkészítése backend szinten | Kész | 00:45 | 2700 | 2024-01-26T18:46:48+01:00 | 2024-01-26T19:31:54+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10168 | COD-122 | Felhasználó lenyíló fül átalakítása a design terv alapján | Kész | 00:30 | 1800 | 2024-01-27T14:48:05+01:00 | 2024-01-27T15:18:18+01:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10171 | COD-129 | Adatbázis optimalizálás | Kész | 00:30 | 1800 | 2024-01-27T15:04:01+01:00 | 2024-01-27T15:34:03+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10167 | COD-130 | Kosár gomb törlése | Kész | 00:10 | 600 | 2024-01-27T15:07:43+01:00 | 2024-01-27T15:17:50+01:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10169 | COD-124 | SVG fájlok lecserélése Font Awesome osztályokra | Kész | 00:10 | 600 | 2024-01-27T15:08:32+01:00 | 2024-01-27T15:18:38+01:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10170 | COD-123 | Bejelentkezés és regisztráció gombok átalakítása a design terv alapján | Kész | 00:10 | 600 | 2024-01-27T15:08:48+01:00 | 2024-01-27T15:18:53+01:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10173 | COD-133 | Navbar javítása | Kész | 00:40 | 2400 | 2024-01-27T15:48:29+01:00 | 2024-01-27T16:28:34+01:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10172 | COD-132 | Bejelentkezés és regisztráció oldal javítása | Kész | 00:15 | 900 | 2024-01-27T15:54:51+01:00 | 2024-01-27T16:09:56+01:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10174 | COD-135 | 3 legújabb játék előkészítése backend szinten | Kész | 00:20 | 1200 | 2024-01-28T13:15:01+01:00 | 2024-01-28T13:35:05+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10175 | COD-136 | Változónevek, metódusok átírása angol nyelvre backend szinten | Kész | 01:00 | 3600 | 2024-01-28T13:38:13+01:00 | 2024-01-28T14:38:18+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10176 | COD-136 | Változónevek, metódusok átírása angol nyelvre backend szinten | Kész | 00:30 | 1800 | 2024-01-28T17:37:27+01:00 | 2024-01-28T18:07:33+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10177 | COD-134 | 3 legújabb játék előkészítése adatbázis szinten | Kész | 00:10 | 600 | 2024-01-29T11:01:36+01:00 | 2024-01-29T11:11:39+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10178 | COD-129 | Adatbázis optimalizálás | Kész | 00:30 | 1800 | 2024-01-29T11:46:01+01:00 | 2024-01-29T12:16:05+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10179 | COD-136 | Változónevek, metódusok átírása angol nyelvre backend szinten | Kész | 00:15 | 900 | 2024-01-30T08:59:44+01:00 | 2024-01-30T09:14:57+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10180 | COD-137 | Apróbb hibák javítása | Kész | 00:50 | 3000 | 2024-01-31T09:36:20+01:00 | 2024-01-31T10:26:36+01:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10181 | COD-136 | Változónevek, metódusok átírása angol nyelvre backend szinten | Kész | 00:25 | 1500 | 2024-02-03T08:56:47+01:00 | 2024-02-03T09:21:56+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10184 | COD-138 | Változónevek, metódusok átírása angol nyelvre adatbázis szinten | Kész | 02:25 | 8700 | 2024-02-03T09:28:42+01:00 | 2024-02-03T11:54:00+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10182 | COD-136 | Változónevek, metódusok átírása angol nyelvre backend szinten | Kész | 01:50 | 6600 | 2024-02-03T10:00:14+01:00 | 2024-02-03T11:51:25+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10183 | COD-129 | Adatbázis optimalizálás | Kész | 00:20 | 1200 | 2024-02-03T11:33:26+01:00 | 2024-02-03T11:53:29+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10185 | COD-140 | Adatbázis diagramm átalakítása | Kész | 00:35 | 2100 | 2024-02-03T21:31:12+01:00 | 2024-02-03T22:06:14+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10186 | COD-138 | Változónevek, metódusok átírása angol nyelvre adatbázis szinten | Kész | 00:13 | 780 | 2024-02-03T22:01:17+01:00 | 2024-02-03T22:14:24+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10191 | COD-139 | Változónevek, metódusok átírása angol nyelvre frontend szinten | Kész | 03:00 | 10800 | 2024-02-05T08:49:39+01:00 | 2024-02-05T11:49:44+01:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10189 | COD-143 | Bestsellerek megtervezése és megvalósítása | Kész | 02:00 | 7200 | 2024-02-05T09:48:55+01:00 | 2024-02-05T11:49:04+01:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10187 | COD-146 | Játék és a termékek javítása backend szinten | Kész | 00:20 | 1200 | 2024-02-05T10:59:14+01:00 | 2024-02-05T11:19:21+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10188 | COD-141 | Adatbázis biztonság optimalizálása | Kész | 00:37 | 2220 | 2024-02-05T11:01:45+01:00 | 2024-02-05T11:38:47+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10190 | COD-144 | Legújabb játékok megtervezése és megvalósítása | Kész | 00:30 | 1800 | 2024-02-05T11:19:15+01:00 | 2024-02-05T11:49:26+01:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10192 | COD-145 | Rendelés és a felhasználó kosara javítása backend szinten | Kész | 00:15 | 900 | 2024-02-06T11:05:52+01:00 | 2024-02-06T11:20:59+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10193 | COD-138 | Változónevek, metódusok átírása angol nyelvre adatbázis szinten | Kész | 00:17 | 1020 | 2024-02-06T21:23:47+01:00 | 2024-02-06T21:40:54+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10194 | COD-147 | Jelszavak biztonságossá tétele backend szinten | Kész | 03:00 | 10800 | 2024-02-11T10:55:43+01:00 | 2024-02-11T13:55:49+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10195 | COD-142 | Carousel megtervezése és megvalósítása | Kész | 01:10 | 4200 | 2024-02-12T12:11:15+01:00 | 2024-02-12T13:21:41+01:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10196 | COD-139 | Változónevek, metódusok átírása angol nyelvre frontend szinten | Kész | 00:20 | 1200 | 2024-02-12T13:02:08+01:00 | 2024-02-12T13:22:09+01:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10197 | COD-149 | Regisztráció oldal hibajavítása | Kész | 00:20 | 1200 | 2024-02-13T12:06:26+01:00 | 2024-02-13T12:26:30+01:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10198 | COD-149 | Regisztráció oldal hibajavítása | Kész | 00:20 | 1200 | 2024-02-13T12:20:14+01:00 | 2024-02-13T12:40:18+01:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10199 | COD-150 | User oldal fetch javítása | Kész | 00:30 | 1800 | 2024-02-13T12:38:08+01:00 | 2024-02-13T13:08:12+01:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10200 | COD-148 | Jelszavak újragenerálása a felhasználó táblában | Kész | 00:38 | 2280 | 2024-02-17T23:57:56+01:00 | 2024-02-18T00:36:00+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10201 | COD-159 | Postman dokumentáció kiegészítése | Kész | 01:30 | 5400 | 2024-02-18T11:57:12+01:00 | 2024-02-18T13:27:28+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10202 | COD-158 | Játékhoz tartozó tárolt eljárások visszaépítése | Kész | 01:13 | 4380 | 2024-02-18T16:16:09+01:00 | 2024-02-18T17:29:24+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10203 | COD-158 | Játékhoz tartozó tárolt eljárások visszaépítése | Kész | 00:14 | 840 | 2024-02-18T17:15:33+01:00 | 2024-02-18T17:29:39+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10204 | COD-148 | Jelszavak újragenerálása a felhasználó táblában | Kész | 00:10 | 600 | 2024-02-18T17:19:50+01:00 | 2024-02-18T17:29:56+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10205 | COD-151 | Admin lehetőség visszaépítése adatbázis szinten | Kész | 00:12 | 720 | 2024-02-18T17:22:58+01:00 | 2024-02-18T17:35:07+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10206 | COD-158 | Játékhoz tartozó tárolt eljárások visszaépítése | Kész | 00:10 | 600 | 2024-02-18T17:40:19+01:00 | 2024-02-18T17:50:22+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10207 | COD-154 | Admin lehetőség visszaépítése backend szinten | Kész | 01:10 | 4200 | 2024-02-19T09:19:21+01:00 | 2024-02-19T10:29:36+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10208 | COD-155 | Játék végpontok visszaállítása | Kész | 01:50 | 6600 | 2024-02-19T11:22:57+01:00 | 2024-02-19T13:13:06+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10209 | COD-160 | Admin jogosultsághoz tartozó tárolt eljárások létrehozása | Kész | 00:34 | 2040 | 2024-02-19T13:38:12+01:00 | 2024-02-19T14:12:16+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10210 | COD-160 | Admin jogosultsághoz tartozó tárolt eljárások létrehozása | Kész | 00:23 | 1380 | 2024-02-19T14:09:12+01:00 | 2024-02-19T14:32:18+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10211 | COD-157 | Frontend hibák javítása | Kész | 02:00 | 7200 | 2024-02-20T07:31:41+01:00 | 2024-02-20T09:31:44+01:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10212 | COD-152 | Játék szerkesztés design megvalósítása | Kész | 00:25 | 1500 | 2024-02-20T09:06:53+01:00 | 2024-02-20T09:31:57+01:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10213 | COD-161 | Bankkártyás fizetés kezdetleges dizájn létrehozása | Kész | 00:15 | 900 | 2024-02-20T09:17:04+01:00 | 2024-02-20T09:32:07+01:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10214 | COD-156 | Játék végpontok védelme | Kész | 00:45 | 2700 | 2024-02-22T09:37:44+01:00 | 2024-02-22T10:22:54+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10215 | COD-159 | Postman dokumentáció kiegészítése | Kész | 00:15 | 900 | 2024-02-22T10:08:10+01:00 | 2024-02-22T10:23:16+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10216 | COD-162 | Hibanapló és információ napló készítés a backenden | Kész | 01:20 | 4800 | 2024-02-24T17:03:30+01:00 | 2024-02-24T18:23:42+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10217 | COD-162 | Hibanapló és információ napló készítés a backenden | Kész | 00:30 | 1800 | 2024-02-25T11:00:28+01:00 | 2024-02-25T11:30:35+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10218 | COD-164 | Bankkártyás fizetés megvalósítása backend szinten | Kész | 03:00 | 10800 | 2024-03-05T08:56:08+01:00 | 2024-03-05T11:55:57+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10219 | COD-165 | JUnit tesztek készítése a Játék végponthoz | Kész | 00:40 | 2400 | 2024-03-05T11:40:38+01:00 | 2024-03-05T12:20:34+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10220 | COD-167 | Végpontok felhasználó azonosítóhoz kötése | Kész | 00:30 | 1800 | 2024-03-07T12:35:06+01:00 | 2024-03-07T13:05:11+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10222 | COD-167 | Végpontok felhasználó azonosítóhoz kötése | Kész | 00:30 | 1800 | 2024-03-07T12:54:02+01:00 | 2024-03-07T13:24:08+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10221 | COD-159 | Postman dokumentáció kiegészítése | Kész | 00:05 | 300 | 2024-03-07T13:00:20+01:00 | 2024-03-07T13:05:31+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10225 | COD-166 | Adminisztrátor oldal összekötése a backenddel | Kész | 04:00 | 14400 | 2024-03-11T07:45:17+01:00 | 2024-03-11T11:45:20+01:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10224 | COD-163 | Adminisztrátor oldal megvalósítása | Kész | 02:00 | 7200 | 2024-03-11T09:44:59+01:00 | 2024-03-11T11:45:06+01:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10227 | COD-157 | Frontend hibák javítása | Kész | 01:20 | 4800 | 2024-03-11T10:25:49+01:00 | 2024-03-11T11:45:58+01:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10223 | COD-159 | Postman dokumentáció kiegészítése | Kész | 00:10 | 600 | 2024-03-11T10:28:46+01:00 | 2024-03-11T10:38:51+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10226 | COD-139 | Változónevek, metódusok átírása angol nyelvre frontend szinten | Kész | 00:40 | 2400 | 2024-03-11T11:05:33+01:00 | 2024-03-11T11:45:35+01:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10228 | COD-168 | Game tárolt eljárás módosítása | Kész | 00:22 | 1320 | 2024-03-11T12:00:19+01:00 | 2024-03-11T12:22:21+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10230 | COD-169 | Fizetés visszatérítés azonosító tárolása | Kész | 00:28 | 1680 | 2024-03-18T14:09:02+01:00 | 2024-03-18T14:37:05+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10229 | COD-159 | Postman dokumentáció kiegészítése | Kész | 00:05 | 300 | 2024-03-18T14:25:38+01:00 | 2024-03-18T14:30:40+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10231 | COD-171 | Fizetés visszatérítés megvalósítása backend szinten | Kész | 00:35 | 2100 | 2024-03-18T14:26:23+01:00 | 2024-03-18T15:01:30+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10232 | COD-170 | Manuális tesztek létrehozása | Kész | 00:42 | 2520 | 2024-03-20T00:35:56+01:00 | 2024-03-20T01:18:00+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10233 | COD-170 | Manuális tesztek létrehozása | Kész | 02:00 | 7200 | 2024-03-20T13:18:39+01:00 | 2024-03-20T15:18:41+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10234 | COD-170 | Manuális tesztek létrehozása | Kész | 00:55 | 3300 | 2024-03-24T23:55:12+01:00 | 2024-03-25T00:50:20+01:00 |  | Bence Kéri | 712020:f1fd9352-978b-4a50-ad8d-d988e590d870 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10235 | COD-173 | Tokent igénylő végpontok optimalizálása | Kész | 01:00 | 3600 | 2024-03-25T15:28:00+01:00 | 2024-03-25T16:28:05+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10236 | COD-159 | Postman dokumentáció kiegészítése | Kész | 00:05 | 300 | 2024-03-25T16:23:12+01:00 | 2024-03-25T16:28:19+01:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10237 | COD-166 | Adminisztrátor oldal összekötése a backenddel | Kész | 02:00 | 7200 | 2024-03-27T20:50:10+01:00 | 2024-03-27T22:50:15+01:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10238 | COD-157 | Frontend hibák javítása | Kész | 02:00 | 7200 | 2024-03-27T20:50:24+01:00 | 2024-03-27T22:50:27+01:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10239 | COD-174 | Hibaüzenetek optimalizálása GET kéréseknél | Kész | 00:30 | 1800 | 2024-04-10T10:32:12+02:00 | 2024-04-10T11:02:17+02:00 |  | Milán Tóth | 712020:0a81de68-7e20-4c9d-88f6-98827dfa6cfe | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10240 | COD-157 | Frontend hibák javítása | Kész | 02:00 | 7200 | 2024-05-09T13:16:50+02:00 | 2024-05-09T15:16:56+02:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0
10241 | COD-175 | Bankkártyás fizetés megvalósítása frontend szinten | Kész | 02:00 | 7200 | 2024-05-09T13:17:03+02:00 | 2024-05-09T15:17:07+02:00 |  | Barnabás Váradi | 712020:e4d81f40-154d-41bb-87f5-1e10a37ef9a7 | COD | CodeCrafters |  |  |  |  | Feladat |  | 0 | 0m | 0